## Team Composition
Team Name: |  | Product Domain/Industry: |  | Project time-line
(Ex. Healthcare)
Member Name |  |  |  | Start Date | End Date
Product Description:
| Coordinator/Lead |  | (Short description of the product) | 2024-02-06 | 2024-04-23

## Product Schedule
| To Do List: |  |  | Review and Notes/Reflections
2024-02-06 | Initial List: |  | Define Team Members
Decide on Team Name
Define Member Roles
Identify Product Domain
Develop Opportunity Statement
Develop Product Description
2024-02-13 | Items Added | Plan Sprint I | Review/refine Product Description
Develop and set team schedule
Develop Product Goals
Evaluate Feasibility and Risks
Review/refine Product Goals
Describe Product for Engineering - V & S document
Review Feature List and prioritize
Allocate tasks for Sprint I
Create Initial Gantt Chart
2024-02-20 | Interim review - Sprint I | Design | Member Feedback on assigned tasks
Update Gantt Chart
2024-02-27 | Interim review - Sprint I | Implement and Test | Member Feedback on assigned tasks
Update Gantt Chart
Update Gantt Chart
2024-03-12 | Sprint I Complete and Presented | Deploy and Plan Sprint II | Present your project progress and outcomes to class; reflections
2024-03-14 | Start Sprint II |  | Review and Prioritize Features
Allocate tasks for Sprint II
Create Initial Gantt Chart
2024-03-21 | Interim review - Sprint II |  | Member Feedback on assigned tasks
Update Gantt Chart
2024-03-28 | Interim review - Sprint II |  | Member Feedback on assigned tasks
2024-04-04 | Sprint II Complete and Presented |  | Present your project progress and outcomes to class; reflections
2024-04-05 | Start Sprint III |  | Review and Prioritize Features
Allocate tasks for Sprint II
Create Initial Gantt Chart
2024-04-09 | Interim review - Sprint III |  | Member Feedback on assigned tasks
2024-04-16 | Interim review - Sprint III |  | Member Feedback on assigned tasks
Update Gantt Chart
2024-04-23 | Sprint III Complete and Presented |  | Present your project progress and outcomes to class; reflections

## Review after Spr-I
Things to present as part of Sprint I; Focus on the pertinent material to the use case(s) | 2022-10-26
| Team Monkey Llama and His Band of Rabid Bananas | Team one | h | Mission: Impossumble
Brief Introduction to your project and team members
UC Diagram(s)
UC Table - with Pre-, Post- conditions, and steps in the UC
Systems sequence diagram - sequence of interactions between the actor and system
Classes identified and participating in the uc(s)
Class relationships
Sequence diagram for the uc(s)
Demo the implementation of uc(s)
Persistent data that is stored and/or retrieved
Project explorer - showing boundary, entity, and control classes
Gantt chart used to track work
What is your one take away - that worked well
What is your one take away - that needs work and improvement

## Product Backlog
Unique UC Log ID | Short User Story | Created by and Date | Reference - what prompted | Relevant Component | Estimate (Hrs.) | Priority | Status
Ex: 5 | Ex: Authorized user wants to view an item | Ex: John, 3/15/19 | Ex: Customer Request | (Ex: UI, Security, DBAccess, ..) | 4 Hrs. | Ex: High, Medium, Low | Ex: Completed, Assigned (Spring #), Backlog

## Analysis
Understanding the Problem
Date | Component | Member Name | Time spent in minutes | Brief description of component

## Component Description
General Description of Components
Name of Component | Describe task pertaining to the of the Component | Team Members responsible

## Design
Creating the Model/UML diagram
Date | Diagram created/updated | Member Name | Time spent in minutes | Brief description of the change

## Writing Code
Writing code
Date | Component and Class affected | Member Name | Time spent in minutes | Brief description of the changes

## Testing
Testing the code
Date | UC tested | Member Name | Time spent in minutes | Brief description of result of test | Issue moved to backlog or handled immediately

## Dashboard
Copyright - Sudharsan Iyengar - August 2017.
Tracking Project Work
| Team Name: |  |  |  |  | Member Contribution |  | Component Effort
Project Description:
| Activity | Time Spent | # of revisits to this activity | Output Artifact (formal and informal) | % of work done by due date | Team Member Name | Total time Spent | Component Name | Total time spent on component
Understanding the problem
Creating a model for the solution
Writing the Code using an IDE (initial)
Testing the code - number of runs
Feedback from testing and completion